## Sheet1
# | Phase | Activity | Stemly | RL | Status | Planned Start Date | Planned End Date | Start Date | Completed Date | Notes | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20
[11 empty] | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
[16 empty] | 1 | [6 empty] | 2 | [6 empty] | 3
1 | Phase I | Kick off Meeting | RA | SCI | completed | 2022-09-12 | 2022-09-12 | 2022-09-12 | 2022-09-12 | bar: 5
2 |  | Workshop: Discovery | RA | RA | started | 2022-09-12 | 2022-09-19 | 2022-09-12 | 2023-02-06 | data transfering and understanding still ongoing. | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
3 |  | Workshop: Solution Details | RA | SCI | started | 2022-09-26 | 2022-09-26 | 2022-10-10 | 2023-02-06 | ongoing - depends on data availability |  |  | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
4 | Phase II | Share Data | I | RA | started | 2022-09-26 | 2022-09-26 | 2022-12-26 | 2023-02-06 | ongoing - challenges to get sell through, ad-spend and market research data | 7: 1; 6: 2; 7: 2; 1: 2; 2: 2; 3: 2; 4: 2; 5: 2
5 |  | EDA & Profiling | RA | SCI | completed | 2022-09-26 | 2022-10-10 | 2022-12-26 | 2023-01-09 |  | 7: 1; 6: 2; 7: 2; 1: 2
6 |  | Data Model and Integration | RA | I | started | 2022-01-31 | 2022-10-17 | 2022-12-26 | 2023-02-06 |  | 6: 2; 7: 2; 1: 2; 2: 2; 3: 2; 4: 2; 5: 2
7 |  | Data Quality Assessment | RA | I | started | 2022-01-17 | 2022-10-17 | 2023-01-02 | 2023-02-06 |  | 7: 2; 1: 2; 2: 2; 3: 2; 4: 2; 5: 2
8 |  | Data Contract Completed | RA | RC | started | 2022-10-17 | 2022-10-17 | 2023-01-02 | 2023-02-06 |  | 3: 1; 7: 2; 1: 2; 2: 2; 3: 2; 4: 2; 5: 2
9 | Phase III | Clustering (TS and Kmeans) | RA | SC | started | 2022-10-10 | 2022-10-17 | 2023-01-02 | 2023-02-06 | iterating over the new data and the new indexes | 2: 1; 7: 2; 1: 2; 2: 2; 3: 2; 4: 2; 5: 2
10 |  | Life Cycle Diffusion Model | RA | I | completed | 2022-10-17 | 2022-01-31 | 2023-01-02 | 2023-01-16 | Replaced with machine learning model - bechmark done. Next iterate with improved model | 3: 1; 7: 2; 1: 2; 2: 2
11 |  | Feature Extraction | RA | I | started | 2022-10-17 | 2022-10-24 | 2023-01-02 | 2023-02-06 | Main features included. To add ad-spend, sell through, MRdata | 3: 1; 7: 2; 1: 2; 2: 2; 3: 2; 4: 2; 5: 2
12 |  | Sell Out ML Forecasting | RA | CI | not started | 2022-10-24 | 2022-10-31 |  |  | data not available | bar: 4
13 |  | Sell In ML Forecasting | RA | I | started | 2022-10-31 | 2022-11-07 | 2023-01-23 | 2023-02-06 | Completed first round for all products and initiatives | 5: 1; 3: 2; 4: 2; 5: 2
14 |  | Configurable Analytics Dashboards | RA | I | started | 2022-10-10 | 2022-11-14 | 2023-01-02 | 2023-02-06 |  | 2: 1; 7: 2; 1: 2; 2: 2; 3: 2; 4: 2; 5: 2
15 |  | Sign Off on Model | RA | CI | not started | 2022-11-14 | 2022-11-14 |  |  | In testing phase | bar: 7
16 | Phase IV | Data loaded in App | RA | CI | started |  |  | 2023-01-30 |  |  | 4: 2
17 |  | Dashboard loaded in App | RA | CI | started |  |  | 2023-01-30 |  |  | 4: 2
18 |  | Dashboard loaded in App | RA | CI | started |  |  | 2023-01-30 | bar: 7
19 |  | Sign Off on Pilot | RA | CI | not started | 2022-11-21 | 2022-11-21 | bar: 1